## Issue Tracker
S.N | Issue | Reported Date | Solve Date | Module | Status | Importancy | Comment
1 | Neighbourhood count in After Operator for First and Last Position | 2018-02-14 |  | Rule Builder | Solved(Tested) | Medium |  | Rule Builder | Pending | High
2 | Neighbourhood count in Before Operator for First and Last Position | 2018-02-14 |  | Rule Builder | Solved(Tested) | Medium |  | Rule Engine | Work In Progress | Medium
3 | Design Rule Engine Setup Page | 2018-02-13 |  | Rule Engine | Solved(Tested) | Medium |  | Service | Rejected | Low
4 | Edit Functionality in Rule Engine Setup | 2018-02-14 |  | Rule Engine | Solved(Not Tested) | Medium |  |  | Solved(Not Tested)
5 | Store Proc to check and Update/Insert in Rule Engine table | 2018-02-14 |  | Rule Engine | Solved(Tested) | Medium |  |  | Not Required
6 | Store Proc to Show common Rule Engine Values(All values from Rule Master, Whether it is present in RuleEndine table or not. | 2018-02-14 |  | Rule Engine | Solved(Tested) | Medium |  |  | Solved(Tested)
7 | "Insured: Mailing Address" not showing the next value with after and first | 2018-03-07 |  | Rule Engine | Pending | Medium |  |  | Hold
8 | Edit functionality in configuration page not working perfectly | 2018-03-07 |  | Rule Engine | Pending | Medium
9 | Data must be saved / Modify the config file value as well as config table value: Configuration page | 2018-03-07 |  | Rule Engine | Pending | Medium
10 | Monthly/Weekly document processing report with graphical format | 2018-03-07 |  | Rule Builder | Pending | Medium
11 | Drildown report with service log and its result | 2018-03-05 | 2018-03-07 | Rule Builder | Solved(Tested) | High
12 | Regex not working as a Operator | 2018-03-07 |  | Rule Builder | Pending | Medium
13 | Validation Rule need to implement. If there is a validation rule(Email/Amount/Number) against a rule then after implementing the rule it will apply the validation rule and save the result Success or failure in DB. | 2018-03-07 |  | Rule Builder | Pending | High
14 | New Page for Validation rule/ we can integrate it in Rule builder page (Need to decide) | 2018-03-07 |  | Rule Builder | Pending | High
15 | API call for BluePrism, BluePrism supply Foldername/FileName/ or the Ruleset to apply the rule and a result will be returned | 2018-03-07 |  | Rule Builder | Pending | High | New Implementation
16 | Tool tip for Dashboard menu | 2018-03-07 | 2018-03-13 | Rule Builder | Solved(Tested) | Low
17 | Web scraping(HTML Agility Pack): Parallal option for reading data from website in place of file upload. May be a radio button(From file/ From Website) | 2018-03-07 | 2018-03-12 | Rule Builder | Solved(Not Tested) | High | New Implementation
18 | Saving of API call(XML/Sql server) (ref. SN. 15) | 2018-03-07 |  | Rule Builder | Pending | High | New Implementation
19 | ApplyRule Edit: Not saving all the values | 2018-03-07 |  | Rule Builder | Pending | Medium
20 | ApplyRule: Choose one document to locate the folder | 2018-03-07 |  | Rule Builder | Pending | Medium
21 | Stop showing '0' with Running status in summary report | 2018-03-08 | 2018-03-08 | Rule Engine | Solved(Tested) | High
22 | Show / Hide fileupload and url provider textbox in document provider radio button. | 2018-03-08 |  | Rule Builder | Pending | High
23 | Implement http://www.redmine.org for issue tracking | 2018-03-12 |  | Rule Builder | Pending | Medium
24 | Modal Popup containing null in time of web scrapping implementation | 2018-03-12 |  | Rule Builder | Pending | Medium
25 | Valid Run ID message in Report Page while click on "0" RunID. | 2018-03-12 |  | Rule Builder | Pending | Medium
26
27
28